## Sheet1
ProjectName: | Developing E-commerce app for Alpha Corporation ltd.
Project Start Date: | 2024-01-08
[7 empty] | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03
Task ID | Activity Name | Assigned To | Dependency | Start | End | Progress | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03
T.01 | Market Research | Jim - Mkt. |  | 2024-07-01 | 2024-07-31 | 100%
T.02 | Product Design | Robert - UI/UX | T.01(FS) | 2024-08-01 | 2024-08-31 | 50%
M.01 | Product Design Finalization | Robert - UI/UX |  | 2024-08-31 | 2024-08-31 | 25% | bar: 2024-08-26
T.03 | Development | Alice - Dev. | T.02(FS) | 2024-09-01 | 2024-10-31 | 10%
M.02 | Development Completion | Alice - Dev. |  | 2024-09-30 | 2024-09-30 | 100% | bar: 2024-09-30
T.04 | Testing | Emma - QA | T.03(FS) | 2024-11-01 | 2024-11-30 | 80%
M.03 | Successful Product Testing | Emma - QA |  | 2024-10-31 | 2024-10-31 | 90% | bar: 2024-10-28
T.05 | Marketing Strategy | Jim - Mkt. | T.03(FS) | 2024-09-01 | 2024-11-30
M.04 | Marketing Strategy Finalization | Jim - Mkt. |  | 2024-11-30 | 2024-11-30 | bar: 2024-11-25
T.06 | Production | Alice - Dev. | T.04(FS) | 2024-12-01 | 2024-12-31
M.05 | Production Completion | Alice - Dev. |  | 2024-12-31 | 2024-12-31 | bar: 2024-12-30
T.07 | Product Launch | Tim - PM | T.04(FS) | 2025-01-01 | 2025-01-31

## Sheet2
Team | Responsibility | Team Responsibility
Marketing Team | Jim | Jim - Mkt.
Project Manager | Tim | Tim - PM
UI/UX Team | Robert | Robert - UI/UX
Software Development | Alice | Alice - Dev.
Quality Assurance | Emma | Emma - QA